## Workstreams
Work-stream | Activity Code | Activity Name | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Progress % | Predecessor Activity | Dependency Type | Priority | Risk Level | Comments / Notes
WS1 | WS1.1.1 | Conduct Change Readiness Assessment & Stakeholder Alignment | 2025-05-15 | 2025-06-15
WS1 | WS1.1.2 | Develop AIS Change Strategy | 2025-05-30 | 2025-07-30
WS1 | WS1.2.1 | Identify & Design Structured Communication Channels | 2025-08-01 | 2025-08-30
WS1 | WS1.3.1 | AIS Executive Briefing Deck | 2025-10-01 | 2025-11-30
WS1 | WS1.3.2 | AIS Awareness Email Campaign | 2025-10-01 | 2025-11-30 |  |  |  | Identify & Design Structured Communication Channels
WS1 | WS1.3.3 | AIS Infographic for Quick Reference | 2025-10-01 | 2025-11-30 |  |  |  | Identify & Design Structured Communication Channels
WS1 | WS1.3.4 | AIS Business Line Impact Reports | 2025-11-01 | 2025-12-31
WS1 | WS1.3.5 | AIS Pilot Success Story Report | 2026-08-01 | 2026-12-31 |  |  |  | Pilot Use Case Identification and Prioritization
WS1 | WS1.3.6 | AIS Change Adoption Dashboard | 2025-10-01 | 2025-11-30 |  |  |  | Develop AIS Change Strategy
WS1 | WS1.3.7 | AIS Transformation Newsletter | 2025-10-01 | 2025-11-30 |  |  |  | Identify & Design Structured Communication Channels
WS1 | WS1.4.1 | Phase 1: Awareness & Basic Training | 2025-07-20 | 2025-07-24
WS1 | WS1.4.2 | Phase 2: Business Line-Specific Deep Dives | 2025-12-16 | 2025-12-20
WS1 | WS1.4.3 | Phase 3: Advanced & Technical Training | 2026-12-16 | 2026-12-20
WS2 | WS2.1 | Align with SEC AIS & Goals | 2025-06-15 | 2026-07-30 |  |  |  | Develop AIS Change Strategy
WS2 | WS2.2 | AIS Governance Charter | 2025-05-15 | 2025-07-15
WS2 | WS2.3 | AIS CE Governance Support | 2025-07-15 | 2027-03-31
WS3 | WS3.1.1 | Identify Data Gaps & Completeness Issues | 2025-07-01 | 2025-10-15
WS3 | WS3.1.2 | Assess Data Standardization & Consistency | 2025-07-01 | 2025-10-15
WS3 | WS3.1.3 | Evaluate Integration & Interoperability Gaps | 2025-07-01 | 2025-10-15
WS3 | WS3.1.4 | Validate Data Governance & Ownership Framework | 2025-07-01 | 2025-10-15
WS3 | WS3.1.5 | Develop AHI Data Framework Operational Gap Report | 2025-10-15 | 2025-11-15
WS3 | WS3.2.1 | Define Target Data Flow & Integration | 2025-10-01 | 2025-11-15
WS3 | WS3.2.2 | Develop Integration Workflow Blueprint | 2025-10-01 | 2025-11-15
WS3 | WS3.3.1 | Pilot Use Case Identification and Prioritization | 2025-08-01 | 2025-09-15
WS3 | WS3.3.2 | Define Pilot Scope & Execution Plan | 2025-09-15 | 2025-10-15
WS3 | WS3.3.3 | Risk Identification & Mitigation Planning | 2025-09-30 | 2025-10-30
WS3 | WS3.4.1 | Assess Existing Data Quality & Completeness | 2025-10-01 | 2026-12-31
WS3 | WS3.4.2 | Develop Data Profiling Reports & Metadata Catalog | 2025-11-01 | 2026-01-31
WS3 | WS3.4.3 | Prepare Business Line Data for Mapping to the CE Unified Model | 2026-01-01 | 2026-03-30
WS3 | WS3.5.1 | Assess Existing Business Line Data Models | 2026-01-01 | 2026-03-30
WS3 | WS3.5.2 | Develop a Unified Logical Data Model Using UML | 2026-01-01 | 2026-02-28
WS3 | WS3.5.3 | Map Business Line-Specific Attributes to the Unified Model | 2026-02-01 | 2026-04-30
WS3 | WS3.6.1 | Develop Data-in-Motion & Data-at-Rest Schemas | 2026-03-01 | 2026-04-15
WS3 | WS3.6.2 | Physical Model Design & Database Implementation | 2026-03-01 | 2026-04-30
WS3 | WS3.6.3 | Map Business Line-Specific Attributes to the Unified Model | 2026-01-01 | 2026-05-31
WS3 | WS3.7.1 | Coordinate with Digital for Setup | 2025-11-01 | 2026-06-30
WS3 | WS3.7.2 | Support in streaming Data Flow | 2026-03-01 | 2026-06-30
WS3 | WS3.8.1 | Future support for AIS Governance Framework | 2026-12-01 | 2027-01-30
WS3 | WS3.8.2 | Propose Scalable Data Architecture requirements | 2026-12-01 | 2027-01-30
WS3 | WS3.8.3 | Define a Business Line Specific AIS Interoperability Strategy | 2027-01-01 | 2027-02-15
WS3 | WS3.8.4 | Propose Phased Implementation & Scaling Plan | 2027-01-01 | 2027-02-15

## Resources
Person Name | Role | Company | Hourly Rate ($) | Total Available Hours | Allocated/Used Hours | Utilization (%) | Comments
Lavjit Singh | PD | EGI |  | 1152 | 25 |  |  | Hours Per Day | 8
Adel Gamal | PM | EGI |  | 1528 | 25
Don Sunny | Senior Consultant | EGI |  | 952 | 25
Ganesh Shinde | Consultant | EGI |  | 952 | 25
Samuel Ezannaya | Consultant | EGI |  | 1536
Stefan Stroobants | Modeling Expert | EGI |  | 600
Jaco Roesch | Modeling Expert | Xtensible |  | 944
Gustav Brand | Data Archiect | Xtensible |  | 944
External Consultant | Modeling Expert | Abjyon |  | 680
Seyed Khali | Change Mgmt Expert | EGI |  | 696

## Budget_vs_Actual
Work-stream | Activity Code | Activity Name | Assigned Person 1 | Allocated Hours Person 1 | Spent Hours Person 1 | Assigned Person 2 | Allocated Hours Person 2 | Spent Hours Person 2 | Planned Budget ($) | Actual Cost ($) | Variance ($) | Progress %
WS1 | WS1.1.1 | Conduct Change Readiness Assessment & Stakeholder Alignment | Lavjit Singh | 100 |  | Adel Gamal
WS1 | WS1.1.2 | Develop AIS Change Strategy | Lavjit Singh |  |  | Adel Gamal
WS1 | WS1.2.1 | Identify & Design Structured Communication Channels | Lavjit Singh |  |  | Adel Gamal
WS1 | WS1.3.1 | AIS Executive Briefing Deck | Lavjit Singh |  |  | Adel Gamal
WS1 | WS1.3.2 | AIS Awareness Email Campaign | Ganesh Shinde |  |  | Samuel Ezannaya
WS1 | WS1.3.3 | AIS Infographic for Quick Reference | Ganesh Shinde |  |  | Samuel Ezannaya
WS1 | WS1.3.4 | AIS Business Line Impact Reports | Lavjit Singh |  |  | Adel Gamal
WS1 | WS1.3.5 | AIS Pilot Success Story Report | Lavjit Singh |  |  | Adel Gamal
WS1 | WS1.3.6 | AIS Change Adoption Dashboard | Lavjit Singh |  |  | Adel Gamal
WS1 | WS1.3.7 | AIS Transformation Newsletter | Lavjit Singh |  |  | Adel Gamal
WS1 | WS1.4.1 | Phase 1: Awareness & Basic Training | Lavjit Singh |  |  | Gustav Brand
WS1 | WS1.4.2 | Phase 2: Business Line-Specific Deep Dives | Lavjit Singh |  |  | Gustav Brand
WS1 | WS1.4.3 | Phase 3: Advanced & Technical Training | Lavjit Singh |  |  | Gustav Brand
WS2 | WS2.1 | Align with SEC AIS & Goals | Lavjit Singh |  |  | Adel Gamal
WS2 | WS2.2 | AIS Governance Charter | Adel Gamal |  |  | Samuel Ezannaya
WS2 | WS2.3 | AIS CE Governance Support | Adel Gamal |  |  | Samuel Ezannaya
WS3 | WS3.1.1 | Identify Data Gaps & Completeness Issues | Don Sunny |  |  | External Consultant
WS3 | WS3.1.2 | Assess Data Standardization & Consistency | Don Sunny |  |  | External Consultant
WS3 | WS3.1.3 | Evaluate Integration & Interoperability Gaps | Don Sunny |  |  | External Consultant
WS3 | WS3.1.4 | Validate Data Governance & Ownership Framework | Don Sunny |  |  | External Consultant
WS3 | WS3.1.5 | Develop AHI Data Framework Operational Gap Report | Don Sunny |  |  | External Consultant
WS3 | WS3.2.1 | Define Target Data Flow & Integration | Gustav Brand |  |  | External Consultant
WS3 | WS3.2.2 | Develop Integration Workflow Blueprint | Gustav Brand |  |  | External Consultant
WS3 | WS3.3.1 | Pilot Use Case Identification and Prioritization | Adel Gamal |  |  | Samuel Ezannaya
WS3 | WS3.3.2 | Define Pilot Scope & Execution Plan | Lavjit Singh |  |  | Adel Gamal
WS3 | WS3.3.3 | Risk Identification & Mitigation Planning | Lavjit Singh |  |  | Adel Gamal
WS3 | WS3.4.1 | Assess Existing Data Quality & Completeness | Gustav Brand |  |  | External Consultant
WS3 | WS3.4.2 | Develop Data Profiling Reports & Metadata Catalog | Gustav Brand |  |  | External Consultant
WS3 | WS3.4.3 | Prepare Business Line Data for Mapping to the CE Unified Model | Gustav Brand |  |  | Stefan Stroobants
WS3 | WS3.5.1 | Assess Existing Business Line Data Models | Gustav Brand |  |  | Stefan Stroobants
WS3 | WS3.5.2 | Develop a Unified Logical Data Model Using UML | Gustav Brand |  |  | Stefan Stroobants
WS3 | WS3.5.3 | Map Business Line-Specific Attributes to the Unified Model | Gustav Brand |  |  | Jaco Roesch
WS3 | WS3.6.1 | Develop Data-in-Motion & Data-at-Rest Schemas | Gustav Brand |  |  | Jaco Roesch
WS3 | WS3.6.2 | Physical Model Design & Database Implementation | Gustav Brand |  |  | Jaco Roesch
WS3 | WS3.6.3 | Map Business Line-Specific Attributes to the Unified Model | Gustav Brand |  |  | Jaco Roesch
WS3 | WS3.7.1 | Coordinate with Digital for Setup | Adel Gamal |  |  | Samuel Ezannaya
WS3 | WS3.7.2 | Support in streaming Data Flow | Adel Gamal |  |  | Samuel Ezannaya
WS3 | WS3.8.1 | Future support for AIS Governance Framework | Lavjit Singh |  |  | Adel Gamal
WS3 | WS3.8.2 | Propose Scalable Data Architecture requirements | Lavjit Singh |  |  | Adel Gamal
WS3 | WS3.8.3 | Define a Business Line Specific AIS Interoperability Strategy | Lavjit Singh |  |  | Adel Gamal
WS3 | WS3.8.4 | Propose Phased Implementation & Scaling Plan | Lavjit Singh |  |  | Adel Gamal

## Risk_Register
Risk ID | Workstream | Activity Code | Activity Name | Risk Description | Risk Category | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Mitigation Plan | Contingency Plan | Owner | Status | Target Resolution Date | Last Updated | Comments
R-001 | WS2 | Governance Charter | Lack of clear data ownership across business lines | Governance | 4 | 4 | 16 | High | Define and agree on data ownership roles with CE and business lines early in the project | Escalate unclear ownership cases to the steering committee for resolution | Data Governance Lead | Open | 2025-06-15 | 2025-05-01
R-002 | WS2 | Governance Charter | Weak data stewardship practices or untrained stewards | Governance | 3 | 3 | 9 | Medium | Deliver training and onboarding for data stewards as part of Change Management | Assign temporary stewards from CE for critical activities | Change Management Lead | Open | 2025-07-01 | 2025-05-01
R-003 | WS3 | Data Profiling | Unidentified data quality issues in legacy systems | Data Quality | 4 | 4 | 16 | High | Start profiling early and prioritize critical asset classes | Scope additional cleansing activities and extend profiling effort if needed | Data Profiling Lead | Open | 2025-08-01 | 2025-05-01
R-004 | WS3 | Data Profiling | Inadequate cleansing and validation tools | Tooling | 3 | 4 | 12 | High | Evaluate profiling toolkits in month 2 and procure early | Use custom scripts and manual validation where needed | IT Integration Lead | Open | 2025-07-15 | 2025-05-01
R-005 | WS2 | Integration Blueprint | OT/IT system incompatibility or protocol mismatch | Integration | 4 | 4 | 16 | High | Validate interfaces and protocol compatibility in the design phase | Introduce middleware solutions to enable translation | Integration Architect | Open | 2025-07-30 | 2025-05-01
R-006 | WS3 | Push-Pull Integration | Lack of real-time integration capability | Integration | 3 | 4 | 12 | High | Define push/pull architecture and run a pilot with sample data | Use batch processing or partial real-time updates where needed | Systems Engineer | Open | 2025-09-01 | 2025-05-01
R-007 | WS3 | Model Customization | Incorrect or incomplete semantic model mapping | Modeling | 3 | 5 | 15 | High | Review mappings with CE and validate against IEC CIM | Allow rework cycles with change control | Data Architect | Open | 2025-10-01 | 2025-05-01
R-008 | WS3 | Scalability Planning | Scalability of pilot results not guaranteed | Deployment | 3 | 4 | 12 | High | Capture scalability indicators during PoC and standardize templates | Plan redesign activities post-pilot with sufficient buffer | Pilot Coordinator | Open | 2026-01-30 | 2025-05-01
R-009 | WS2 | Change Management | Business resistance to new roles and responsibilities | Organizational | 3 | 4 | 12 | High | Engage stakeholders early and reinforce role clarity in communications | Adjust role assignments and introduce change champions | Change Lead | Open | 2025-07-01 | 2025-05-01
R-010 | WS2 | Communication Strategy | Communication plan is not effectively executed | Change Management | 2 | 4 | 8 | Medium | Define message cadence and use multi-channel engagement | Trigger intensive sessions or campaign relaunch | Comms Lead | Open | 2025-06-30 | 2025-05-01
R-011 | WS2 | Staffing & Delivery | Limited availability of skilled consultants or SMEs | Resourcing | 4 | 4 | 16 | High | Pre-confirm availability and assign backups in contract | Use external support or adjust timeline milestones | PMO | Open | 2025-06-01 | 2025-05-01
R-012 | WS3 | Tooling & Profiling | Tooling limitations for data profiling or integration | Technology | 3 | 4 | 12 | High | Assess tool requirements early and secure access in Phase 1 | Implement Python/Excel workarounds or explore open-source tools | Tech Lead | Open | 2025-07-15 | 2025-05-01

## Issue_Tracker
Issue ID | Workstream | Activity Name | Issue Description | Reported By | Assigned To | Date Reported | Severity | Impact Area | Root Cause | Resolution Plan | Target Resolution Date | Status | Actual Resolution Date | Escalated (Yes/No) | Comments / Updates

## Milestones
Milestone ID | Milestone Name | Workstream | Linked Activities | Planned Date | Actual Date | Owner | Status | Delay (Days) | Critical (Yes/No) | Dependencies | Comments / Notes
D1.1 | Change Management Plan (report) | WS1 |  | 2025-07-15
D1.2 | CE AIS Communication Strategy (report) | WS1 |  | 2025-09-30
D1.3 | Basic Awareness / Executive Awareness CE Communication Engagement Materials | WS1 |  | 2025-11-30
D1.4 | Basic Awareness and CE Training Materials | WS1 |  | 2025-12-30
D1.5 | Business Deep Dive amd CE Communication Engagement Materials | WS1 |  | 2026-06-30
D1.6 | Advanced / Technical CE and Communication Engagement Materials | WS1 |  | 2026-11-30
D2 | D2.1 AIS Implementation Governance Charter | WS2 |  | 2025-08-30
D3.1 | AHI Data Framework Operational Gap and Integration Assessment (Report / Presentation) | WS3 |  | 2025-11-30
D3.2 | Data Flow & Workflow Integration Blueprint | WS3 |  | 2026-01-30
D3.3 | Pilot Selection & Execution Planning Blueprint | WS3 |  | 2026-01-01
D3.4 | BL Data Catalog Report | WS3 |  | 2026-03-01
D3.5 | CE – BL Unified Model (UML Diagram) | WS3 |  | 2026-05-30
D3.6 | Push Pull Integration Workflow & Integration Validation Report | WS3 |  | 2026-07-30
D3.7 | Data Architecture Blueprint / Guideline as annexure to System Integration/Procurement | WS3 |  | 2027-01-30

## Sheet1 (hidden)
WS1.1.1 | Conduct Change Readiness Assessment & Stakeholder Alignment
WS1.1.2 | Develop AIS Change Strategy
WS1.2.1 | Develop AIS Messaging Framework
WS1.2.1 | Identify & Design Structured Communication Channels
WS1.3.1 | AIS Executive Briefing Deck
WS1.3.2 | AIS Awareness Email Campaign
WS1.3.3 | AIS Infographic for Quick Reference
WS1.3.4 | AIS Business Line Impact Reports
WS1.3.5 | AIS Pilot Success Story Report
WS1.3.6 | AIS Change Adoption Dashboard
WS1.3.7 | AIS Transformation Newsletter
WS1.4.1 | Phase 1: Awareness & Basic Training
WS1.4.2 | Phase 2: Business Line-Specific Deep Dives
WS1.4.3 | Phase 3: Advanced & Technical Training
WS2.1 | Align with SEC AIS & Goals
WS2.2 | AIS Governance Charter
WS2.3 | AIS CE Governance Support
WS3.1.1 | Identify Data Gaps & Completeness Issues
WS3.1.2 | Assess Data Standardization & Consistency
WS3.1.3 | Evaluate Integration & Interoperability Gaps
WS3.1.4 | Validate Data Governance & Ownership Framework
WS3.1.5 | Develop AHI Data Framework Operational Gap Report
WS3.2.1 | Define Target Data Flow & Integration
WS3.2.2 | Develop Integration Workflow Blueprint
WS3.3.1 | Pilot Use Case Identification and Prioritization
WS3.3.2 | Define Pilot Scope & Execution Plan
WS3.3.3 | Risk Identification & Mitigation Planning
WS3.4.1 | Assess Existing Data Quality & Completeness
WS3.4.2 | Develop Data Profiling Reports & Metadata Catalog
WS3.4.3 | Prepare Business Line Data for Mapping to the CE Unified Model
WS3.5.1 | Assess Existing Business Line Data Models
WS3.5.2 | Develop a Unified Logical Data Model Using UML
WS3.5.3 | Map Business Line-Specific Attributes to the Unified Model
WS3.6.1 | Develop Data-in-Motion & Data-at-Rest Schemas
WS3.6.2 | Physical Model Design & Database Implementation
WS3.6.3 | Map Business Line-Specific Attributes to the Unified Model
WS3.7.1 | Coordinate with Digital for Setup
WS3.7.2 | Support in streaming Data Flow
WS3.8.1 | Future support for AIS Governance Framework
WS3.8.2 | Propose Scalable Data Architecture requirements
WS3.8.3 | Define a Business Line Specific AIS Interoperability Strategy
WS3.8.4 | Propose Phased Implementation & Scaling Plan